## Sheet1
COSC1076 ¦ Semester 1 2021
Assignment 2 ¦ Weekly Update Tracking Sheet
Group Name: | APT Dudes
Group Member: | Amandeep Hothi |  | Progress Classes: | Ahead
Group Member: | Karan Pradhan |  |  | On-track
Group Member: | Rhys Puclin |  |  | Behind
Group Member: | Nguyen Duc Phu |  |  | Way Behind
Tutor:
Class:
|  | Week 7 | Goals | Tutor Notes | Indidvidual Updates | Amandeep Hothi | Karan Pradhan | Rhys Puclin | Nguyen Duc Phu
|  |  | Group Formed |  | Weekly Contribution
|  |  | MS Team created |  | Issues | No issues
|  |  | Git Repo created |  | Other Notes | MS Team Created and Git repo Created as a group
|  | Progress | On-track
|  | Week 8 | Goals | Tutor Notes | Indidvidual Updates | Amandeep Hothi | Karan Pradhan | Rhys Puclin | Nguyen Duc Phu
|  |  | Choice of where to use linked list, vector & array |  | Weekly Contribution | Main menu, User promt | Linked List implementation | ADT implementation for storing information, game loop logic not required | Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required
|  |  | Initial Design of ADTs (classes and potential methods) |  | Issues | No issues
|  |  | Main menu |  | Other Notes
User Prompt (for gameplay), but no/minimal error checking
Linked List implementation
Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required
ADT implementation for storing information, game loop logic not required
|  | Progress | On-track
|  | Week 9 | Goals | Tutor Notes | Indidvidual Updates | Amandeep Hothi | Karan Pradhan | Rys Puclin | Nguyen Duc Phu
|  |  | Load/Save to/from data strucutres (doesn't require integration with main menu or game loop) |  | Weekly Contribution | Load/Save game | Write test cases for common use. And some part of the placing tiles for the game play. | Gameplay for single round, that is selecting and moving of tiles from a factory to players mosaic | Initialisation of data strctures for new game
|  |  | Initialisation of data strctures for new game |  | Issues | Unable to create a seemless fromat to load the game. Issues with libraries | No issues
|  |  | Write Tests Cases for common uses |  | Other Notes
Gameplay for single round, that is selecting and moving of tiles from a factory to players mosaic
|  | Progress | Behind
|  | Week 10 | Goals | Tutor Notes | Indidvidual Updates | Amandeep Hothi | Karan Pradhan | Rys Puclin | Nguyen Duc Phu
|  |  | Fully complete implementation and error free |  | Weekly Contribution | Group Report | Final tests and Fully complete implementation and error free. | Load/Save game, Full error checking of user prompt, Fully complete implementation and error free, all possible player inputs implemeted | Full error checking of user prompt, Fully complete implementation and error free, Automated placement of tiles at end of round, but no scoring Refactor, add utils, break down code for readability and memory leak check
|  |  | Full error checking of user prompt |  | Issues | No issues | whike testing we got some few errors which we fixed after testing our test cases for example our outfile was showing the input commands in te output fiile which we fixed, also while we were placing out tile we were having some minor issues in the test cases which we fixed as well. rest tests went quiet smooth. | Had some difficulty with allowing spaces in user input, making correct tile-placing logic, and methods not changing variables as expected. | Had some part still need refactor, game logic while placing tile could be implemented more elegantly and easier to read. Placing two exact same tiles next to each other doesnt seem to work. Couple of minor bugs and edges case havent covered yet.
|  |  | Automated placement of tiles at end of round, but no scoring |  | Other Notes |  | Free of mermory leak. | All issues resolved except for some fringe cases. For example, if the tile bag is empty and the player has no valid moves, the player will not be able to make a move. Also, an unknown bug sometimes causes a segmentation fault when a tile is placed in the corner of the board.
|  |  | Final Tests |  |  |  |  | Implementation complete
Group Report Written
|  | Progress | Ahead